## BugReport
Bug ID | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Additional Information | Screenshots/Attachments
Bug ID_001 | The registration form allows special characters in the First Name and Last Name fields without displaying an error message, resulting in invalid data acceptance. | 1. Enter special characters in the First Name and Last Name fields (e.g., @#). 2. Fill in other required fields correctly. 3. Click the "Continue" button. | An error message should appear indicating that invalid characters are not allowed in the First Name and Last Name fields. | No error message is displayed when invalid characters (e.g., numbers, special symbols) are entered in the name fields, allowing the form to accept invalid inputs. | Major | High | The issue could lead to invalid data being stored in the database, which may affect other functionalities like user search, name display, or data export.
Bug ID_002 | When the network connection is lost during form submission, no error message is displayed, and the user is not informed of the connection failure. | 1. Enter valid details in all required fields on the Registration page. 2. Disconnect the network before submitting the form. 3. Click the "Continue" button. | An error message should be displayed about the network connection failure, and data entered by the user should be preserved. | No error message was displayed when the network connection failed, leaving the user unaware of the issue. | Major | High | This bug can lead to poor user experience, as the user might lose the entered data and not understand why the form is not submitted.
Bug ID_003 | When the network connection is lost during form submission, no error message is displayed, and the user is not informed of the connection failure. | 1. Enter valid details in all required fields on the Registration page. 2. Disconnect the network before submitting the form. 3. Click the "Continue" button. | An error message should be displayed about the network connection failure, and data entered by the user should be preserved. | No error message was displayed when the network connection failed, leaving the user unaware of the issue. | Major | High | This bug can lead to poor user experience, as the user might lose the entered data and not understand why the form is not submitted.
Bug ID_004 | The application does not display an error message or prompt when the session times out during registration, leading to a poor user experience as the form submission fails silently. | 1. Leave the registration page open for a prolonged period to simulate a session timeout. 2. Enter valid details and submit the form. | The system should display an error message or prompt the user to refresh the page after session timeout. | No error message or prompt is shown when the session times out, leaving the user unaware of the session expiration. | Major | Medium | No error message or prompt is shown when the session times out, leaving the user unaware of the session expiration.
Bug ID_005 | After submitting a "Forgot Password" request with a registered email address, no confirmation message is displayed to the user, leaving them uncertain whether the request was successful. | 1. Click on the "Forgot Password" link on the Login page. 2. Enter a registered email address. 3. Click Continue. | A confirmation message should be displayed, informing the user that a password reset email has been sent. | No confirmation message is displayed after submitting the request, creating confusion for the user. | Major | Medium | This issue may result in users submitting multiple reset requests or abandoning the process due to a lack of feedback.
Bug ID_006 | The "eye" icon for toggling password visibility is missing on the Login page, preventing users from viewing their password while typing. | 1. Enter a valid Email. 2. Enter a Password. 3. Click the "eye" icon to toggle password visibility. | The password should become visible when toggled and hidden when toggled back. | No "eye" icon is visible to toggle password visibility. | Minor | Low | This issue impacts the user experience by making it difficult to confirm the entered password.
Bug ID_007 | No error message is displayed after multiple failed login attempts, and the user is allowed to continue entering incorrect credentials without any restrictions or warnings. | 1. Enter incorrect credentials multiple times (e.g., 5 times). 2. Click the Login button each time. | The system should display an error message indicating an account lockout or warn the user after multiple failed login attempts. | No error message is displayed, and the user is allowed to re-enter login details without restriction. | Major | High | This could lead to security vulnerabilities, as there is no limitation on login attempts.
Bug ID_008 | After submitting a "Forgot Password" request with a registered email address, no confirmation message is displayed to the user, leaving them uncertain whether the request was successful. | 1. Click on the "Forgot Password" link on the Login page. 2. Enter a registered email address. 3. Click Continue. | A confirmation message should be displayed, informing the user that a password reset email has been sent. | No confirmation message is displayed after submitting the request, creating confusion for the user. | Major | Medium | This issue may result in users submitting multiple reset requests or abandoning the process due to a lack of feedback.
Bug ID_009 | After closing the browser without logging out, the user remains logged in when the browser is reopened, which poses a security risk by not requiring a fresh login. | 1. Log in with valid credentials. 2. Close the browser without logging out. 3. Reopen the browser and revisit the site. | The user should be logged out, requiring a new login upon reopening the browser. | The user remains logged in, without being prompted to log in again. | Major | High | This could lead to unauthorized access if someone else accesses the same device.
Bug ID_010 | After entering a valid registered email address on the "Forgot Password" page, no success message is displayed, leaving users uncertain whether the password reset email has been sent. | 1. Go to the "Forgot Password" page. 2. Enter a valid registered email address. 3. Click on "Continue." | A success message "An email with a password reset link has been sent" should be displayed. | No success message was displayed indicating that “An email with a password reset link has been sent.” | Major | Medium | This can cause confusion and lead users to think that the request was unsuccessful, resulting in multiple submissions.
Bug ID_011 | After performing the password reset request, no email is received at the registered email address, leaving users unaware that the password reset process was initiated. | 1. Perform TC_FP_002 (Submit a valid email address for password reset). 2. Open the email inbox of the registered email. 3. Verify if a password reset email is received. | The user should receive an email containing the password reset link. | No email was received on the registered email address, leaving users unaware that the password reset process was initiated. | Major | High | This issue may prevent users from successfully resetting their passwords, causing frustration and loss of access.
Bug ID_012 | Because no email was received on the registered email address, the operation to verify the password reset link functionality cannot be performed. | 1. Open the password reset email. 2. Click on the reset link. | The user should be redirected to a page where they can enter a new password. | Unable to perform this operation due to no email receipt, thus the password reset link cannot be verified. | Major | High | This issue highlights a cascading problem stemming from the failure to receive the password reset email, affecting the entire password recovery process.
Bug ID_013 | The action to set a new password cannot be performed as no password reset email was received, and the reset link could not be opened. | 1. Open the reset link. 2. Enter a new password and confirm it. 3. Click on "Submit." | The new password should be saved, and the user should be able to log in with the new password. | The action to set a new password could not be performed due to the absence of the password reset email. | Major | High | This issue stems from the failure to receive the reset email, preventing further steps in the password reset process.
Bug ID_014 | The error message for mismatched passwords could not be verified as no password reset email was received, preventing the password reset link from being opened. | 1. Open the reset link. 2. Enter a new password. 3. Enter a different password in the confirmation field. 4. Click "Submit." | An error message "Password confirmation does not match password!" should be displayed. | Unable to perform the action due to the absence of the password reset email, and thus the reset link could not be opened. | Major | Medium | This issue is part of the larger problem of not receiving the password reset email, preventing the entire password recovery process from functioning.
Bug ID_015 | The verification of the error message for a weak password cannot be performed as no password reset email was received, preventing access to the password reset link. | 1. Open the reset link. 2. Enter a weak password (e.g., less than 4 characters). 3. Click on "Submit." | An error message "Password must be between 4 and 20 characters!" should be displayed. | Unable to perform the action due to the absence of the password reset email, and thus the reset link could not be opened. | Major | Medium | This issue is tied to the failure to receive the password reset email, which blocks further steps in the password recovery process.
Bug ID_016 | When searching for products within a specific category, no products are displayed, and the message "There is no product that matches the search criteria" is shown, even though matching products exist. | 1. Navigate to a specific category. 2. Use the search bar to enter a product name. 3. Click on the "Search" button. | Search results should display products within the selected category that match the search term. | No product is shown in search results, and the message "There is no product that matches the search criteria" is displayed despite the presence of matching products. | Major | High | This issue could be related to incorrect search indexing or filtering in the application.
Bug ID_017 | During guest checkout, the user can successfully place an order without creating an account, but no order confirmation email is received, leading to a lack of confirmation for the user. | 1. Add a product to the cart. 2. Proceed to checkout without logging in. 3. Select the guest checkout option. 4. Complete the checkout. | The user should be able to order products without creating an account, and an order confirmation email should be sent. | The user can complete the order without an account, but no order confirmation email is received. | Major | High | This issue could cause confusion for users as they won't receive any confirmation that the order has been successfully placed.
Bug ID_018 | When attempting to set an invalid product quantity (0 or negative value) in the cart, the system does not display a validation error or reset the quantity to 1. Users can proceed with invalid quantities, which could lead to order processing issues. | 1. Add a product to the cart. 2. Navigate to the cart. 3. Attempt to set the product quantity to 0 or a negative value. | The system should display a validation error or reset the quantity to 1, preventing the user from proceeding with invalid quantities. | No validation error is displayed, the quantity is not reset to 1, and the system does not prevent the user from proceeding with invalid quantities. | Major | High | This issue could cause confusion for users as they won't receive any confirmation that the order has been successfully placed.
Bug ID_019 | Users are unable to generate a printable invoice or downloadable PDF for their orders because the "Print Invoice" or "Download PDF" options are not available on the order history page. | 1. Navigate to "Order History". 2. Select an order. 3. Click on "Print Invoice" or "Download PDF". | A printable invoice or downloadable PDF for the order should be generated. | The page does not provide a "Print Invoice" or "Download PDF" option for the order, preventing users from generating a printable or downloadable invoice. | Major | High | This issue impacts user experience as customers may need a record of their orders in a printable format for their reference.
Bug ID_020 | Users are unable to attach supporting files (e.g., photos) when submitting a return request, as there is no option available on the return request page. | 1. Log in to the user account. 2. Select a product for return. 3. Attach supporting files (e.g., photo of the product). 4. Submit the request. | The system should accept file attachments and allow the user to submit proof along with the return request. | There is no option seen on this page to accept file attachments, preventing users from submitting proof with their return request. | Major | High | This issue may hinder the return process for users who need to provide evidence for their return requests.
Bug ID_021 | The system does not allow users to select and return multiple products from the same order in a single return request, forcing users to submit separate requests for each product. | 1. Log in to the user account. 2. Go to “Order History”. 3. Select multiple products for return from the same order. 4. Submit the request. | The system should allow the user to return multiple products from the same order in a single return request. | The system did not allow the user to return multiple products from the same order in a single return request. | Major | High | This limitation can lead to increased user frustration and additional processing overhead for handling multiple return requests separately.